## Bug Report
Defect ID | Module | Summary | Severity | Priority | Status
BUG-01 | Booking | Double booking allowed for same dates | Critical | P1 | Closed
BUG-02 | Payment | Booking created despite payment failure | Critical | P1 | Closed
BUG-03 | Cancellation | Incorrect refund amount calculated | High | P1 | Closed
BUG-04 | Search | Unavailable properties shown in search | High | P2 | Closed
BUG-05 | Host Earnings | Earnings not updated after refund | High | P2 | Closed
BUG-06 | Auth | Session not expiring after timeout | Medium | P3 | Closed
BUG-07 | Security | Guest can access host dashboard via URL | Critical | P1 | Closed
BUG-08 | Reviews | Guest allowed to review without stay | Medium | P3 | Closed
BUG-09 | Admin | Suspended users still able to login | Critical | P1 | Closed
BUG-10 | UI | Booking confirmation email delayed | Low | P4 | Closed

## Details
Field | Details | Severity | Meaning
Defect ID | BUG-01 | Critical | Core business flow broken
Module | Booking | High | Major feature not working
Summary | System allows booking for already booked dates | Medium | Partial functionality issue
Description | Guest is able to book a property for dates that are already confirmed by another guest | Low | UI or cosmetic issue
Steps to Reproduce | 1. Guest A books property for 10–12 May2. Guest B selects same dates3. Proceeds to booking
Expected Result | System should block second booking
Actual Result | Booking confirmed for Guest B | Priority | Meaning
Severity | Critical | P1 | Fix immediately
Priority | P1 | P2 | Fix before release
Status | Closed | P3 | Fix if time permits
Root Cause | Availability check missing before payment | P4 | Can be deferred
Resolution | Availability check missing before payment
Retest Status | Passed
Defect ID | BUG-02
Module | Payment
Summary | Booking created even when payment fails
Steps | 1. Select property2. Enter invalid card3. Click Pay
Expected | Booking should not be created
Actual | Booking created with “Pending” payment
Severity | Critical
Priority | P1
Status | Closed
Defect ID | BUG-03
Module | Cancellation
Summary | Refund not matching cancellation policy
Expected | Refund calculated as per policy
Actual | Flat refund applied
Severity | High
Priority | P1
Status | Closed
Defect ID | BUG-07
Module | Security
Summary | Guest can access host dashboard via direct URL
Expected | Access denied
Actual | Host dashboard loads
Severity | Critical
Priority | P1
Status | Closed
Fix | Role-based authorization enforced